## Tabelle1
Todo:

Powerups		3
Lasers		3
Moving walls		4
Maps + tutorial		5
Score system		1
Online		4
Patching system		4
Community map browser		7
Rating system		3
Blender tutorials		2
How to store / Community maps		3
Community map system		5
Website		10
Blog		2
Social media		2
Soundtracks		2
Variety		2
UI		10
Cheat prevention		5
Beta testing		2
Achievements		4

	Result:	154.00	days
		5.05	months
		0.42	years